# Milo AI Pet Robot

Quest Journey Product Roadmap for a Raspberry Pi 5 + OpenAI companion robot

| Document | quest-journey.docx | Version | v1.0 |
| --- | --- | --- | --- |
| Project Type | Hardware + AI pet robot | Primary Prototype | Raspberry Pi 5 |
| Team Roles | AI Developer, Coder, Hardware Developer | Roadmap Horizon | Prototype to MVP |

# Product Vision

Build a small expressive AI pet robot that reacts to touch, voice, mood, and user bonding. The first lovable moment is simple: when the user pats the head, the pet becomes happy, smiles through its eyes, moves gently, and says a warm line.

Prototype principle: prove the pet feels alive before adding complex mobility.

Core loop: sensors create events, the behavior engine updates mood, actions drive face, motion, and voice.

AI role: conversation, personality, memory, and action selection; local code handles instant reactions.

# Role Ownership

| Role | Primary Ownership | Key Deliverables |
| --- | --- | --- |
| AI Developer | Personality, conversation, memory, mood rules, OpenAI integration | Prompt system, tool/function definitions, memory schema, voice response logic |
| Coder | Raspberry Pi app, event loop, integrations, tests, logging | main.py, behavior engine, action router, audio/display/servo/sensor modules |
| Hardware Developer | Electronics, power, physical build, sensor and actuator placement | BOM, wiring diagram, stable power, screen/mic/speaker/servo mounting |

# Roadmap Phases

| Phase | Duration | Outcome | Exit Criteria |
| --- | --- | --- | --- |
| 0. Definition | 1-2 weeks | Character, features, BOM, safety rules | Approved scope and first demo script |
| 1. Desk Prototype | 3-5 weeks | Touch, face, voice, one servo | Head pat happy reaction works end to end |
| 2. Animatronic Prototype | 4-6 weeks | Head/ear motion and richer moods | Five moods with matching face and movement |
| 3. Mobile MVP | 6-10 weeks | Wheels, obstacle sensing, app settings | 30-minute stable demo with voice and movement |
| 4. Beta Device | 2-4 months | Custom PCB/enclosure, OTA, user profiles | Beta users can run the robot safely at home |
| 5. Production Prep | 3-6 months | Certification, QA jigs, manufacturing | Pilot production package ready |

# Quest Journey

## Quest 1: Happy Head Pat

| Field | Details |
| --- | --- |
| Goal | Create the first full-system emotional reaction. |
| Success Condition | Touch head -> mood becomes happy -> happy eyes -> gentle movement -> voice says a short happy line. |
| AI Developer | Define happy personality line, mood update rule, and allowed actions. |
| Coder | Implement touch event, mood update, display action, servo action, and audio playback. |
| Hardware Developer | Wire touch sensor, display, speaker, and one servo with stable external servo power. |

## Quest 2: Voice Companion

| Field | Details |
| --- | --- |
| Goal | Let the pet listen and reply naturally. |
| Success Condition | User speaks -> robot understands -> robot replies with voice and matching expression. |
| AI Developer | Build OpenAI voice flow, response constraints, and pet-like speech style. |
| Coder | Connect mic capture, speaker output, session handling, and logs. |
| Hardware Developer | Mount mic/speaker, reduce noise, and confirm audio levels in the enclosure. |

## Quest 3: Emotion Engine

| Field | Details |
| --- | --- |
| Goal | Make behavior stateful instead of command-only. |
| Success Condition | Robot changes between neutral, happy, sleepy, curious, and scared based on events. |
| AI Developer | Define mood transitions, energy, bond, and memory rules. |
| Coder | Implement robot_state.py and behavior_engine.py with tests. |
| Hardware Developer | Map each mood to safe mechanical limits and test repeated motion. |

## Quest 4: Expressive Face

| Field | Details |
| --- | --- |
| Goal | Give the pet readable eyes and idle life. |
| Success Condition | Happy, sleepy, curious, sad, and idle animations render smoothly. |
| AI Developer | Define expression triggers and emotional timing. |
| Coder | Implement display rendering, animation loop, and expression API. |
| Hardware Developer | Choose and mount the screen; verify viewing angle and cable strain relief. |

## Quest 5: Body Movement

| Field | Details |
| --- | --- |
| Goal | Translate feelings into physical motion. |
| Success Condition | Happy wiggle, sleepy tilt, curious look-around, and scared freeze/recoil all work safely. |
| AI Developer | Design movement personality and action vocabulary. |
| Coder | Implement servo controller, action router, and calibration script. |
| Hardware Developer | Install servos, define angle limits, and validate power draw. |

## Quest 6: Memory And Bond

| Field | Details |
| --- | --- |
| Goal | Let the pet remember the user and become warmer over time. |
| Success Condition | Robot remembers user name, preferences, and bond level across restarts. |
| AI Developer | Design memory fields and privacy rules. |
| Coder | Save/load local memory and expose it to prompts safely. |
| Hardware Developer | Support testing; no major hardware change required. |

## Quest 7: Wake And Sleep

| Field | Details |
| --- | --- |
| Goal | Make idle behavior feel alive and power-aware. |
| Success Condition | Robot sleeps, blinks, wakes on name/touch, and reacts differently when energy is low. |
| AI Developer | Define idle, sleep, and wake personality. |
| Coder | Implement idle loop, wake triggers, and battery-aware behavior. |
| Hardware Developer | Test heat, battery stability, and long idle runs. |

## Quest 8: Demo Mode

| Field | Details |
| --- | --- |
| Goal | Create a reliable 2-minute showcase. |
| Success Condition | Robot wakes, reacts to pat, answers a question, moves cutely, and returns to idle. |
| AI Developer | Prepare scripted conversation and fallback lines. |
| Coder | Add demo mode command and deterministic action sequence. |
| Hardware Developer | Make body presentable and robust for repeated demonstrations. |

# First 30-Day Sprint Plan

| Week | AI Developer | Coder | Hardware Developer |
| --- | --- | --- | --- |
| 1 | Personality spec, prompt draft, action list | Project skeleton, event bus, state model | BOM, wiring plan, order parts |
| 2 | Happy reaction rules and voice line set | Touch sensor + display happy eyes | Wire touch sensor, display, one servo |
| 3 | OpenAI voice session and tool-calling plan | Mic/speaker integration and action router | Audio mounting and servo calibration |
| 4 | Demo script and memory v0 | End-to-end Happy Head Pat demo | Clean prototype body and power stability test |

# MVP Acceptance Checklist

Head pat reaction completes in under one second for local face and motion feedback.

Voice conversation works reliably with clear mic input and speaker output.

At least five moods are visible through face, voice, and movement.

Robot can run for 30 minutes without crashing or rebooting.

Servo power is isolated from Raspberry Pi power, with common ground connected.

Logs capture sensor events, mood changes, AI requests, and hardware errors.

User memory is stored locally and can be reset.

The demo mode is repeatable without manual code edits.

# Recommended Repository Focus

For the first prototype, keep the implementation narrow. The most important files are the main app, robot state, behavior engine, touch sensor, face expressions, audio I/O, OpenAI client, realtime voice, and servo controller.

| Area | Starter Files |
| --- | --- |
| Core | src/main.py, src/core/robot_state.py, src/core/behavior_engine.py |
| AI | src/ai/openai_client.py, src/ai/realtime_voice.py, src/config/personality.yaml |
| Hardware I/O | src/sensors/touch_sensor.py, src/actuators/servo_controller.py |
| Feedback | src/display/expressions.py, src/audio/microphone.py, src/audio/speaker.py |

# Immediate Next Quest

Start with Quest 1: Happy Head Pat.

Definition of done: the user touches the head sensor, the robot detects touch, changes mood to happy, shows happy eyes, moves head or ears, and says: "Hehe, that feels nice."